## Munkalap1
sprint	category	sub-category	name
1	code		level calorie counter
1	code		timer
1	art	character	lips
1	code		lips controls
1	code		lips gravity
1	code		lips eat
1	code		lips hit the ground
1	art	character	burger
1	art	character	hotdog
1	art	character	bun
1	art	character	sausage
1	art	character	pizza
1	art	character	fries
1	art	character	cola
1	art	character	donut
1	art	character	ice cream cone
1	art	character	ice cream bar
1	art	character	purple pickle
1	code		lips regurgitation particles
1	code		eaten food list
1	art	effect	purple pickle left over
1	art	effect	burger left-over
1	art	effect	bun left-over
1	art	effect	sausage left-over
1	art	effect	pizza left-over
1	art	effect	fries left-over
1	art	effect	cola left-over
1	art	effect	donut left-over
1	art	effect	ice cream cone left-over
1	art	effect	ice cream bar left-over
1	code		lips eat crumbs particles
1	art	effect	crumbs
1	art	scenery	pavement
1	code		lips hit the ground dust particles
1	art	effect	dust
1	code		food list generator
1	art	UI	burger counter icon
1	art	UI	hotdog counter icon
1	art	UI	bun counter subicon
1	art	UI	sausage counter subicon
1	art	UI	pizza counter icon
1	art	UI	pizza slice counter icon
1	art	UI	fries counter icon
1	art	UI	cola counter icon
1	art	UI	donut counter icon
1	art	UI	ice cream cone counter icon
1	art	UI	ice cream bar counter icon
1	art	UI	title
1	art	UI	subtitle
1	code		title neon blinking animation
1	code		subtitle 3d splat and slip animation
1	code		subtitle splat drop particles
1	art	effect	subtitle splat drops
1	code		credits button settings
1	code		start game button settings
1	code		level data processor
1	data		level 1 data
1	data		level 2 data
1	data		level 3 data
1	data		level 4 data
1	data		level 5 data
1	data		level 6 data
1	data		level 7 data
1	code		hotdog splitting
1	code		pizza splitting
1	code		rewards generation

2	art	UI	start game button art
2	art	UI	credits button art
2	code		burger counter icon pulse on change
2	code		hotdog counter icon pulse on change
2	code		bun counter icon pulse on change
2	code		sausage counter icon pulse on change
2	code		pizza counter icon pulse on change
2	code		fries counter icon pulse on change
2	code		cola counter icon pulse on change
2	code		donut counter icon pulse on change
2	code		ice cream cone counter icon pulse on change
2	code		ice cream bar counter icon pulse on change
2	code		level calorie upload highest
2	code		total calorie counter
2			Weekly Gobble front page
2
2
2
2
2
3	art		timer custom fonts
3
3
3
3
3
3
3
3
3
3